## GanttChart
Project Development | Reported by | Assigned to | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
|  |  | 09/01 - 9/07 | 09/08 - 09/14 | 09/15 - 09/21 | 09/22 - 09/28 | 09/29 - 10/05 | 10/06 - 10/12 | 10/13 - 10/19 | 10/20 - 10/26 | 10/27 - 11/02 | 11/03 - 11/09 | 11/10 - 11/16 | 11/17 - 11/23 | 11/24 - 11/30 | 12/01 - 12/07
Phase 1
SRS Document |  |  | Week 3: Start of Phase 1
1. Purpose | Wail | Wail, Yesenia
2. Overall Description | Wail | Wail
3. Specific Requirments | Wail | Wail, Yesenia, Shichang, Emmanuel
4. Non-Functional Requirments | Wail | Wail, Yesenia, Shichang, Emmanuel
5. Use Cases | Wail | Wail, Yesenia, Shichang, Emmanuel
6. UML Class Diagrams | Wail | Wail
7. UML Sequence Diagrams | Wail | Wail
8. Meeting Minutes | Wail | Yesenia, Wail
8. Gantt Chart | Wail | Wail | bar: Week 7
9. Project Presentation Slides | Wail | Yesenia | bar: Week 7
10. Project Presentation | Wail | All | Week 7: Phase 1 Deliverables Due (10/01)
Phase 2
Design Phase
Phase 3
Implementation Phase
Final Submission
Final Presentation