## GanttChart
Project Development | Reported by | Assigned to | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
|  |  | 09/01 - 9/07 | 09/08 - 09/14 | 09/15 - 09/21 | 09/22 - 09/28 | 09/29 - 10/05 | 10/06 - 10/12 | 10/13 - 10/19 | 10/20 - 10/26 | 10/27 - 11/02 | 11/03 - 11/09 | 11/10 - 11/16 | 11/17 - 11/23 | 11/24 - 11/30 | 12/01 - 12/07
Phase 1
SRS Document |  |  | Week 3: Start of Phase 1
1. Purpose | Wail | Wail, Yesenia | bar: Week 3 to Week 7
2. Overall Description | Wail | Wail | bar: Week 3 to Week 7
3. Specific Requirments | Wail | Wail, Yesenia, Shichang, Emmanuel | bar: Week 3 to Week 7
4. Non-Functional Requirments | Wail | Wail, Yesenia, Shichang, Emmanuel | bar: Week 3 to Week 7
5. Use Cases | Wail | Wail, Yesenia, Shichang, Emmanuel | bar: Week 3 to Week 7
6. UML Class Diagrams | Wail | Wail | bar: Week 3 to Week 7
7. UML Sequence Diagrams | Wail | Wail | bar: Week 3 to Week 7
8. Meeting Minutes | Wail | Yesenia, Wail | bar: Week 3 to Week 7
8. Gantt Chart | Wail | Wail | bar: Week 7
9. Project Presentation Slides | Wail | Yesenia, Wail | bar: Week 7
10. Project Presentation | Wail | All | Week 7: Phase 1 Deliverables Due (10/01)
Phase 2 |  |  | Week 8: Start of Phase 2
Design Phase | bar: Week 8 to Week 11
1.Product Scope and overview | Wail | Wail | bar: Week 8 to Week 9
2. Architecture Design (Client– Server, System Modules, Data Flow) | Wail | Wail | bar: Week 9 to Week 11
3. Class candidates and diagrams | Wail | Wail, Yesenia, Shichang, Emmanuel | bar: Week 9 to Week 11
4. Prototype Design | Wail | Yesenia, Shichang | bar: Week 10 to Week 11
5. UML Diagram Development (Use Case, Class, Sequence) | Wail | Wail, Yesenia, Shichang | bar: Week 10 to Week 11
6. Design Review & Verification | Wail | Wail | bar: Week 10 to Week 11
7. Finalize Design Document | Wail | Wail, Shichang | bar: Week 10 to Week 11
8. Meeting Minutes | Wail | Yesenia | bar: Week 8 to Week 11
8. Gantt Chart | Wail | Emmanuel | bar: Week 10 to Week 11
9. Project Presentation Slides | Wail | Yesenia, Wail | bar: Week 10 to Week 11
10. Project Presentation | Wail | Wail, Yesenia, Shichang, Emmanuel | bar: Week 11
11. Project Schedule Update | Wail | Emmanuel | Week 11: Phase 2 Deliverables Due (10/29)
Phase 3 |  |  | Week 12: Start of Phase 2
Implementation Phase | bar: Week 12 to Week 14
1.System Manager Class | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 12 to Week 14
2.Data Manager Class | Yesenia | Wail | bar: Week 12 to Week 14
3. Course, Schedule, University Classes | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 12 to Week 14
4.User, Student, Admin Classes | Yesenia | Yesenia, Shichang | bar: Week 12 to Week 14
5. GUI Classes | Yesenia | Shichang, Yesi | bar: Week 12 to Week 14
6. Message, MessageType, Status, UserType | Yesenia | Wail | bar: Week 12 to Week 14
7. Server and Client Classes | Yesenia | Wail | bar: Week 12 to Week 14
8. Reporting Class |  | Wail, Shichang, Emmanuel | bar: Week 12 to Week 14
Phase 4
Testing Phase
1. Add test file for SystemManager | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 12 to Week 15
2. Add test file for DataManager | Yesenia | Wail | bar: Week 12 to Week 15
3. Add test file for Course, Schedule, University Classes | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 12 to Week 15
4. Add test file for User, Student, Admin Classes | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 12 to Week 15
5. Add test file for GUI Classes | Yesenia | Shichang, Yesi | bar: Week 12 to Week 15
6. Add test file for Message, MessageType, Status, UserType | Yesenia | Wail | bar: Week 12 to Week 15
7. Add test file for Server and Client Classes | Yesenia | Wail | bar: Week 12 to Week 15
8. Add test file for Reporting Class | Yesenia | Wail, Shichang, Emmanuel | bar: Week 12 to Week 15
9. Test port fowarding | Yesenia | Yesenia | bar: Week 14 to Week 16
10. Update Design Document | Yesenia | Wail, Shichang | bar: Week 15 to Week 16
11. Meeting Minutes | Yesenia | Yesenia | bar: Week 12 to Week 16
12. Gantt Chart | Yesenia | Yesenia | bar: Week 15 to Week 16
13. Project Presentation Slides | Yesenia | Yesenia, Wail | bar: Week 15 to Week 16
14. Project Presentation | Yesenia | Wail, Yesenia, Shichang, Emmanuel | bar: Week 15 to Week 16
15. Project Schedule Update | Yesenia | Emmanuel, Wail | bar: Week 12; Week 15 to Week 16
Final Submission |  |  | Week 14: Phase 2 Deliverables Due (10/29)
Final Presentation |  |  | Week 14: Final Presentation on 12/01